## Sheet1
Main Business Question: Sub-Question A: Which game characteristics (genre, platform, release year, ESRB rating, critic score, etc.) most strongly explain variation in user scores? → Regression + feature importance Sub-Question B: Can we predict whether a user review is positive or negative using transformer embeddings and text modeling? → Classification + text embeddings Sub-Question C: Can we identify clusters of games with similar user perception using metadata, review embeddings, and sales information? → Unsupervised clustering (k-means / PCA / BERTopic optional)
# | Task Name | Start | Deadline | Status | Member | Description | Notebook | Comments
1 | Form business question | 27/11 | 2025-02-12 |  | All | Each member writes 2 proposals for the main business question.
2 | Form sub-questions | 27/11 | 2025-02-12 |  | All | Each member drafts 3–5 sub-questions.
3 | Define Modeling Targets per Sub-question | 27/11 | 29/11 |  | All | Each member needs to clarify: 1. What exactly they are predicting (the target variable)? 2. Which features they will use (input features)? 3. Which type of model they will build? 4. Why this modeling approach matches the sub-question?
4 | Standardise titles across datasets | 27/11 | 29/11 |  | Rosie | Lowercase, trim, remove special characters. | EDA
5 | Verivy Delimiter and encoding | 27/11 | 29/11 |  | Rosie | Use something like # Save with pipe delimiter and real NULLs (empty cells) df.to_csv(output_path, sep="¦", index=False, na_rep="", encoding="utf-8") | EDA
6 | metaClean dataset analysis | 27/11 | 29/11 | Not Started | Jun | Load dataset and inspect structure: 1. Inspect missing values - Compute % missing; plot bar chart 2. Categorical profiling (platform/genre/rating) - Value counts + rare category identification 3. Numerical profiling (scores) - Visualize user, critic, meta score distributions 4. Validate title & ID consistency - Detect inconsistent IDs/titles 5. Clean missing categorical values - Impute missing platform/genre with mode 6. Clean invalid numeric values - Fix invalid user/critic scores; remove outliers | EDA | Follow the same format as Debarati
7 | UserReviews dataset analysis | 27/11 | 29/11 |  | Rosie | Inspect user review columns: 1. Inspect missing values (UR) - Identify missing texts or user scores 2. Review text length analysis (UR) - Add text_length_words + histogram 3. Distribution of UR user scores - Create histogram + boxplot 4. Remove empty or nonsense reviews - Flag reviews < 3 words; remove | EDA | Follow the same format as Debarati
8 | ExpertReviews dataset analysis | 27/11 | 29/11 |  | Rosie | Inspect critic text and critic_score: 1. Missing critic text inspection - Find short or empty critic reviews 2. Critic score distribution - Histogram, boxplot 3. Critic review text length analysis - Compute text length; plot distribution 4. Identify inconsistent titles (ER vs metaClean) - Create mismatch list 5. Remove empty reviews | EDA | Follow the same format as Debarati
9 | sales dataset analysis | 27/11 | 29/11 |  | Iro | Load sales; inspect schema: 1. Validate numeric sales columns - Ensure all sales >= 0 and numeric, otherwise convert to float, fix negatives 2. Check missing values (sales) - Identify missing per region 3. Sales distribution analysis - Histograms for NA/EU/JP/global sales 4. Check sales title alignment with metaClean - Match titles and generate fuzzy mapping | EDA | Follow the same format as Debarati
10 | Create master title/ID key dictionary | 29/11 | 2025-01-12 |  | Rosie | Mapping file linking four datasets. | EDA
11 | Merge metaClean + UR | 29/11 | 2025-01-12 |  |  | Left join by title/id; validate rows. | EDA
12 | Merge ER into master dataset | 29/11 | 2025-01-12 |  |  | Join critic reviews; document mismatches. | EDA
13 | Merge sales into master dataset | 29/11 | 2025-01-12 |  |  | Join using cleaned mapping keys. | EDA
14 | Validate master dataset | 2025-01-12 | 2025-02-12 |  |  | Check NA counts, duplicates, row counts. | EDA
15 | Correlation heatmap | 2025-01-12 | 2025-02-12 |  |  | Correlations: scores, lengths, sales. | EDA
16 | Genre vs User Score boxplots | 2025-02-12 | 2025-03-12 |  |  | Grouped score distribution. | EDA
17 | Platform vs User Score comparison | 2025-02-12 | 2025-03-12 |  |  | Boxplots + ANOVA. | EDA
18 | Scatter: User Score vs Critic Score | 2025-02-12 | 2025-03-12 |  |  | Scatter + trendline. | EDA
19 | Sales vs User Score relationships | 2025-02-12 | 2025-03-12 |  |  | Scatter for NA/EU/JP/global sales. | EDA
20 | Outlier detection | 2025-02-12 | 2025-03-12 |  |  | IQR + Z-score; document removed points. | EDA
21 | Encode categorical variables | 2025-04-12 | 2025-06-12 |  |  | OHE/frequency encoding. | EDA
22 | Scale numeric variables | 2025-04-12 | 2025-06-12 |  |  | StandardScaler for numeric columns. | EDA
23 | Clean user review text | 2025-04-12 | 2025-06-12 |  |  | Remove punctuation, stopwords, lowercase. | EDA
24 | Clean critic review text | 2025-04-12 | 2025-06-12 |  |  | Same cleaning pipeline. | EDA
25 | Compute user review sentiment | 2025-04-12 | 2025-06-12 |  |  | Polarity score using VADER/TextBlob. | EDA
26 | Additional metadata features | 2025-04-12 | 2025-07-12 |  |  | Add release decade, tags, etc. | EDA
27 | Compute review length features | 2025-06-12 | 2025-07-12 |  |  | text_length_words, char counts. | EDA
28 | Write sub conclusions and explanations based on EDA notebook from Debarati | 27/11 | 2025-07-12 |  | All |  | EDA
29 | Generate user review embeddings |  |  |  |  | Use SBERT or HF transformer. | Modeling
30 | Generate critic review embeddings |  |  |  |  | Create critic embeddings with transformer. | Modeling
31 | Dimensionality reduction (PCA/SVD) |  |  | Not Started | Jun | Reduce embeddings to 50–200 dims. | Modeling
32 | Train/val/test split for A-model |  |  | Not Started | Jun | Split predicting user_score. | Modeling
33 | Train baseline model (A) |  |  | Not Started | Jun | Linear regression. | Modeling
34 | Train Random Forest (A) |  |  | Not Started | Jun | RF on metadata features. | Modeling
35 | Evaluate A-model |  |  | Not Started | Jun | RMSE/MAE + plots. | Modeling
36 | Create binary labels for B-model |  |  |  |  | user_score >= 7 ⇒ positive. | Modeling
37 | Train baseline classifier (B) |  |  |  |  | Logistic regression. | Modeling
38 | Train RF classifier (B) |  |  |  |  | RF using embeddings. | Modeling
39 | Train NN classifier (B) |  |  |  |  | Train feedforward NN. | Modeling
40 | Select clustering features (C) |  |  |  |  | Choose metadata + PCA embeddings. | Modeling
41 | PCA for cluster visualization |  |  |  |  | Reduce to 2D/3D. | Modeling
42 | Run k-means clustering |  |  |  |  | Choose k via elbow method. | Modeling
43 | Interpret clusters |  |  |  |  | Describe characteristics of each cluster. | Modeling
44 | SHAP for A-model |  |  |  |  | SHAP values for RF. | Modeling
45 | SHAP for B-model |  |  |  |  | SHAP for text classifier. | Modeling
46 | Cluster explainability (C-model) |  |  |  |  | Use PCA loadings to interpret clusters. | Modeling
47 | Generate evaluation visualizations |  |  |  |  | Confusion matrix, regression plot, cluster visualizations. | Modeling
48 | Consolidate model comparisons |  |  |  |  | Summary of all three models. | Modeling
49 | BERTopic topic modeling |  |  |  |  | Extract topics from UR texts. | Modeling
50 | Clustering on embeddings |  |  |  |  | k-means on reduced embeddings. | Modeling
51 | Polish EDA Notebook (Notebook 1) and ask feedback |  | 18/12 | Not Started | Jun | Markdown, structure, explanations. | EDA
52 | Polish Modeling Notebook (Notebook 2) and ask feedback |  | 18/12 |  |  | Cleanup, markdown, visuals. | Modeling